## Project Log
Project Log
Project: Office relocation • Manager: Bilal Ahmed • Start: 01 Oct 2026
# | Date | Type | Description | Raised by | Owner | Priority | Due date | Status | Resolution / notes | Summary
1 | 01-Oct-2026 | Decision | Move date confirmed for 14 Dec | Sponsor | Bilal | High | 01-Oct-2026 | Closed | Approved in kickoff meeting | Open
2 | 05-Oct-2026 | Task | Get three quotes from movers | Bilal | Sana | High | 15-Oct-2026 | Closed | Quotes received; vendor B chosen | In progress
3 | 09-Oct-2026 | Risk | Network cabling not ready at new site | IT | Usman | High | 20-Nov-2026 | Open | Contractor booked for 10 Nov | Closed
4 | 12-Oct-2026 | Issue | Lease start date differs from contract | Finance | Bilal | Medium | 25-Oct-2026 | Closed | Landlord corrected the date | Total entries
5 | 18-Oct-2026 | Change | Add two meeting rooms to floor plan | HR | Sana | Medium | 30-Oct-2026 | In progress | Awaiting cost estimate
6 | 22-Oct-2026 | Task | Order new desks and chairs | Sana | Sana | Medium | 10-Nov-2026 | In progress | PO raised
7 | 27-Oct-2026 | Risk | Staff parking limited | HR | Ayesha | Low | 30-Nov-2026 | Open | Survey staff travel needs
8 | 28-Oct-2026 | Issue | Old printer lease ends early | IT | Usman | Low | 15-Nov-2026 | Open | Request extension