Project Status Report

Reporting period: 26 Oct – 01 Nov 2026

| Project | CRM system rollout |
| --- | --- |
| Project manager | Nadia Hussain |
| Sponsor | Operations Director |
| Report date | 02 Nov 2026 |

| Overall | Schedule | Budget | Scope |
| --- | --- | --- | --- |
| ON TRACK | AT RISK | ON TRACK | ON TRACK |

Summary

•  Data migration completed for 3 of 4 regions; user training started on schedule.

Accomplishments this period

•  Migrated customer records for North, South and Central regions

•  Completed training for 42 of 120 users

•  Approved final report templates

Milestones

| Milestone | Due | Status | % complete |
| --- | --- | --- | --- |
| Data migration | 06 Nov | In progress | 75% |
| User training | 20 Nov | In progress | 35% |
| Go-live | 01 Dec | Not started | 0% |

Risks and issues

| Risk / issue | Impact | Action and owner |
| --- | --- | --- |
| East region data has duplicates | Medium – may delay migration 1 week | Clean-up script; IT team by 05 Nov |
| Trainer availability in late Nov | Low | Book backup trainer; HR |

Budget

Approved: 2,400,000   •   Spent to date: 1,310,000 (55%)   •   Forecast at completion: 2,350,000

Next period plan and decisions needed

•  Complete East region migration

•  Train 40 more users

•  Decision: approve weekend go-live window (Sponsor)